## Hoja1
WBS | Fase | Descripción | Fecha Inicio | Fecha Fin | Trabajo (días) | Costo Estimado MX
Fase 0 – Arquitectura
Fase 1 – Análisis
Fase 2 – Diseño
Fase 3 – Desarrollo
Fase 4 – Pruebas
Fase 5 – Producción
Total Estimado
0 | Definición Arquitectónica | Talleres, análisis de alternativas PI, CPI/BTP o híbrida, definición de arquitectura y ambientes | 2026-06-23 | 2026-06-23 | 15
1 | Análisis y Levantamiento | Análisis funcional y técnico completo | 2026-07-27 | 2026-08-21 | 20
1.1 | Análisis ECC vs S/4HANA | Identificación de diferencias técnicas y APIs | 2026-07-27 | 2026-07-31 | 5
1.2 | Reglas actuales ECC | Documentación de reglas vigentes | 2026-08-03 | 2026-08-07 | 5
1.3 | Reglas S/4HANA | Talleres funcionales y definición de reglas nuevas | 2026-08-10 | 2026-08-14 | 5
1.4 | Control de origen | Diseño de control entre cajas ECC y S/4 | 2026-08-17 | 2026-08-21 | 5
2 | Diseño Técnico | Diseño funcional y técnico detallado | 2026-08-24 | 2026-09-18 | 20
2.1 | Diseño Aplicación | Router, trazabilidad, datos y reglas | 2026-08-24 | 2026-09-04 | 10
2.2 | Diseño Integración | Diseño PI, CPI/BTP o híbrido | 2026-09-07 | 2026-09-18 | 10
3 | Desarrollo | Construcción de aplicación e integraciones | 2026-09-21 | 2026-11-20 | 45
3.1 | Desarrollo Aplicación | Router, reglas, SAT, trazabilidad | 2026-09-21 | 2026-10-30 | 30
3.2 | Desarrollo Integración | Integración PI/CPI/BTP/API REST | 2026-11-02 | 2026-11-20 | 15
4 | Pruebas | Validación integral del sistema | 2026-11-23 | 2026-12-18 | 20
4.1 | Unitarias e Integración | Validación técnica y funcional | 2026-11-23 | 2026-11-27 | 5
4.2 | End-to-End | Flujo completo ECC y S/4 | 2026-11-30 | 2026-12-04 | 5
4.3 | Regresión ECC | Validación de no afectación | 2026-12-07 | 2026-12-11 | 5
4.4 | UAT | Pruebas con usuarios Heineken | 2026-12-14 | 2026-12-18 | 5
5 | Producción y Estabilización | Go-live, monitoreo y soporte | 2026-12-21 | 2027-01-15 | 20
5.1 | Deploy Producción | Ejecución de despliegue | 2026-12-21 | 2026-12-23 | 3
5.2 | Hypercare | Soporte intensivo post salida | 2026-12-28 | 2027-01-15 | 17
|  | Concepto | Costo USD
|  | Fase 0 – Arquitectura | 18000
|  | Fase 1 – Análisis | 24000
|  | Fase 2 – Diseño | 28000
|  | Fase 3 – Desarrollo | 85000
|  | Fase 4 – Pruebas | 24000
|  | Fase 5 – Producción | 18000
|  | Total Estimado | 197,000 USD

## DNA 4.0 Proposal
ID | Task Name | Duration | Start | Finish | Predecessors | Resource Names |  | Weight
1 | Architectural Definition | 13 days | Tue 6/23/26 | Thu 7/9/26 |  |  | Phase 0 | 40%
2 | Integration platform definition | 2 days | Tue 6/23/26 | Wed 6/24/26 |  | Both
3 | Communication protocol definition (SOAP/API/REST) | 3 days | Tue 6/23/26 | Thu 6/25/26 |  | Both
4 | Exposure/Ingestion roles definition | 2 days | Fri 6/26/26 | Mon 6/29/26 | 2,3 | Both
5 | Webservice/API content confirmation | 4 days | Tue 6/30/26 | Fri 7/3/26 | 4 | Both
6 | Confirmation of NO Changes with Konesh | 2 days | Mon 7/6/26 | Tue 7/7/26 | 5 | Heineken
7 | Documentation of Zyphers supported by S4 server | 2 days | Wed 7/8/26 | Thu 7/9/26 | 6 | Heineken
8 | Busines Logic Definition | 13 days | Tue 6/23/26 | Thu 7/9/26
9 | Current Business Rules review | 4 days | Tue 6/23/26 | Fri 6/26/26 |  | Both
10 | S4 expected scenarios | 4 days | Tue 6/23/26 | Fri 6/26/26 |  | Both
11 | S4 Business Rules definition | 5 days | Mon 6/29/26 | Fri 7/3/26 | 10,9 | Both
12 | Test cases / Scope definition | 4 days | Mon 7/6/26 | Thu 7/9/26 | 11 | Heineken
13 | Functionality development | 25 days | Fri 7/10/26 | Thu 8/13/26 | 1,8 |  | Phase 1 | 30%
14 | DB structure (Tables & Stored Procedures) | 6 days | Fri 7/10/26 | Fri 7/17/26 |  | DNA 4.0
15 | Business Rules for records in Konesh | 5 days | Mon 7/20/26 | Fri 7/24/26 | 14 | DNA 4.0
16 | Business Rules for records not found in Konesh | 4 days | Mon 7/27/26 | Thu 7/30/26 | 15 | DNA 4.0
17 | Business Rules for records not found in S4 | 4 days | Mon 7/27/26 | Thu 7/30/26 | 15 | DNA 4.0
18 | Data flow Control for two boxes requests | 4 days | Fri 7/31/26 | Wed 8/5/26 | 16,17 | DNA 4.0
19 | Error Management | 2 days | Thu 8/6/26 | Fri 8/7/26 | 18 | DNA 4.0
20 | Test cases preparation | 11 days | Mon 7/20/26 | Mon 8/3/26 | 14 | Heineken
21 | Unit Testing & Documentation | 10 days | Fri 7/31/26 | Thu 8/13/26 | 16,17 | DNA 4.0
22 | Integration Development | 30 days | Mon 7/20/26 | Fri 8/28/26 | 14
23 | Webservice/API interfaces with S4 | 7 days | Mon 7/20/26 | Tue 7/28/26
24 | DNA 4.0 | 6 days | Mon 7/20/26 | Mon 7/27/26 |  | DNA 4.0
25 | Heineken | 7 days | Mon 7/20/26 | Tue 7/28/26 |  | Heineken
26 | Double flow control adjustments for ECC | 8 days | Tue 7/28/26 | Thu 8/6/26 | 24 | DNA 4.0
27 | Recurrency | 5 days | Fri 8/7/26 | Thu 8/13/26 | 26 | DNA 4.0
28 | Error management | 3 days | Fri 8/14/26 | Tue 8/18/26 | 27 | DNA 4.0
29 | Unit Testing | 8 days | Wed 8/19/26 | Fri 8/28/26 | 28 | DNA 4.0
30 | S4 test environment preparation | 10 days | Mon 8/17/26 | Fri 8/28/26 |  | Heineken
31 | Integral & User Testing | 60 days | Tue 6/23/26 | Mon 9/14/26 |  |  | Phase 2 | 20%
32 | Test Cases Preparation | 5 days | Mon 8/31/26 | Fri 9/4/26 | 13,22
33 | Exist in Konesh, and solved with Konesh | 5 days | Mon 8/31/26 | Fri 9/4/26 |  | Heineken
34 | Exist in Konesh, requires S4 validation | 5 days | Mon 8/31/26 | Fri 9/4/26 |  | Heineken
35 | Exists in S4, unique record found - all scenarios | 5 days | Mon 8/31/26 | Fri 9/4/26 |  | Heineken
36 | Exists in S4, multiple records found - all scenarios | 5 days | Mon 8/31/26 | Fri 9/4/26 |  | Heineken
37 | Do not exist in S4 | 5 days | Mon 8/31/26 | Fri 9/4/26 |  | Heineken
38 | End to End interfacing testing | 5 days | Tue 6/23/26 | Mon 6/29/26 |  | Both IT
39 | Test Cases execution | 4 days | Mon 9/7/26 | Thu 9/10/26 | 32,38
40 | Exist in Konesh, and solved with Konesh | 4 days | Mon 9/7/26 | Thu 9/10/26 |  | Both
41 | Exist in Konesh, requires S4 validation | 4 days | Mon 9/7/26 | Thu 9/10/26 |  | Both
42 | Exists in S4, unique record found - all scenarios | 4 days | Mon 9/7/26 | Thu 9/10/26 |  | Both
43 | Exists in S4, multiple records found - all scenarios | 4 days | Mon 9/7/26 | Thu 9/10/26 |  | Both
44 | Do not exist in S4 | 4 days | Mon 9/7/26 | Thu 9/10/26 |  | Both
45 | Functionality adjustmens | 2 days | Fri 9/11/26 | Mon 9/14/26 | 39 | DNA 4.0
46 | Integral Testing documentation | 2 days | Fri 9/11/26 | Mon 9/14/26 | 39 | DNA 4.0
47 | Go-Live | 0 days | Tue 6/23/26 | Tue 6/23/26 |  |  | Phase 3 | 10%
48 | Based on Heineken Releasing calendar